## Project Tracker
Project Tracker
|  |  | Percent Over/Under to Flag: | 25%
[5 empty] | in hours | in days
Task | Category | Assigned To | Est. Start | Est. Finish | Est. Work | Est. Duration | BLANK | Actual Start | Actual Finish | Actual Work | Actual Duration | Notes
Create MOCKUP Customer Order (PNG) | Design | Nguyễn Thị Yên Thịnh | 2013-01-18 | 2013-01-18 | 2 | 0.25 |  | 2013-01-18 | 2013-01-18 | 2 | 0
Create MOCKUP Customer Order (HTML) | Design | An Ngọc Anh | 2013-01-19 | 2013-01-20 | 6 | 0.75 |  | 2013-01-19 | 2013-01-20 | 0 | 1
Create MOCKUP Tracking Order for Customer (PNG) | Design | Nguyễn Thị Yên Thịnh | 2013-01-18 | 2013-01-18 | 2 | 0.25 |  | 2013-01-18 | 2013-01-18 | 2 | 0
Create MOCKUP Tracking Order for Customer (HTML) | Design | Nguyễn Đỗ Vượng | 2013-01-19 | 2013-01-20 | 4 | 0.5 |  | 2013-01-18 | 2013-01-18 | 4 | 0
Draw UseCase Diagram (EAP) | Design | Nguyễn Thị Yên Thịnh | 2013-01-20 | 2013-01-21 | 4 | 0.5 |  | 2013-01-20 | 2013-01-20 | 2 | 0 | Chưa review
Review UseCase Diagram (EAP) | Design | Nguyễn Hoàng Việt Khánh | 2013-01-21 | 2013-01-21 | 1 | 0.125 |  |  |  | 510 | 0
Create Sample Code for AutoSchedule (SLN) | Coding | Nguyễn Hoàng Việt Khánh | 2013-01-19 | 2013-01-21 | 10 | 1.25 |  | 2013-01-19 |  | 790 | -40699 | Xong 75% tính năng, chờ mockup AutoSchedule_DetailCollectionPlanView để gắn vào là ok
Create Proposal for Auto Pricing for Orders (DOC) | Design | Nguyễn Đỗ Vượng | 2013-01-20 | 2013-01-21 | 4 | 0.5 |  | 2013-01-21 | 2013-01-21 | 6 | 0 | Xong DOC, đang design màn hình
Create Proposal for Auto Pricing for Orders (DOC) | Design | Nguyễn Thị Yên Thịnh | 2013-01-21 | 2013-01-21 | 4 | 0.5 |  | 2013-01-21 | 2013-01-21 | 1 | 0 | Chuyển qua làm việc khác
Create MOCKUP AutoSchedule_DetailCollectionPlanView (HTML) | Design | An Ngọc Anh | 2013-01-21 | 2013-01-21 | 4 | 0.5 |  | 2013-01-21 |  |  | -40701 | Trễ so với deadline. Do chưa hiển thị được 2 popup. Commit hôm nay phải xong
Create BASIC DESIGN for AutoSchedule (DOC) | Design | Nguyễn Hoàng Việt Khánh | 2013-01-21 | 2013-01-22 | 6 | 0.75 |  | 2013-01-21 | 2013-01-21 | 4 | 0 | Có thay đổi nên phần này sẽ được replan lại
Create Report 2 (DOC) | Reporting | Nguyễn Hoàng Việt Khánh | 2013-01-21 | 2013-01-24 | 8 | 1 |  |  |  |  | 0 | Trễ so với deadline. Do bận phải làm các task research
Update Business For AutoSchedule (DOC) | Design | Nguyễn Hoàng Việt Khánh | 2013-01-22 | 2013-01-24 | 2 | 0.25 |  |  |  |  | 0
Draw State Diagram for Order status (EAP) | Design | Nguyễn Thị Yên Thịnh | 2013-01-22 | 2013-01-22 | 2 | 0.25 |  | 2013-01-22 | 2013-01-22 | 2 | 0
Create MOCKUP for Customer(order tracking) (HTML) | Design | An Ngọc Anh | 2013-01-22 | 2013-01-23 | 4 | 0.5 |  | 2013-01-22 |  |  | -40702
Search Internet for Big Delivery Company Pricing Formula (DOC) | Research | Nguyễn Đỗ Vượng | 2013-01-22 | 2013-01-22 | 4 | 0.5 |  | 2013-01-22 |  |  | -40702 | Không có công thức public. Contact với thầy để tìm solution
Search Internet for Big Delivery Company Pricing Formula (DOC) | Research | Nguyễn Thị Yên Thịnh | 2013-01-22 | 2013-01-22 | 2 | 0.25 |  |  |  |  | 0
Import DB OSM into SQL Server and How to Work with it (SLN) | Research | Nguyễn Hoàng Việt Khánh | 2013-01-22 | 2013-01-23 | 6 | 0.75 |  | 2013-01-22 | 2013-01-23 | 6 | 1 | Can't use Postgre
Link all MOCKUP together (Logically + Elegantly) (HTML) | Design | An Ngọc Anh | 2013-01-23 | 2013-01-23 | 2 | 0.25 |  |  |  |  | 0
Create Plugin Demo (SLN) | Coding | Nguyễn Đỗ Vượng | 41297 | 41301 | 16 | 2 |  |  |  |  | 0
Research about Accounting Module for Users(Hub, Tiktak Staff, Vendor) (DOC) | Research | Nguyễn Thị Yên Thịnh | 2013-01-23 | 2013-01-25 | 10 | 1.25 |  |  |  |  | 0
Create Vendor's Management Item function (SLN) | Coding | Nguyễn Đỗ Vượng | 2013-01-25 | 2013-01-27 | 12 | 1.5 |  |  |  |  | 0
Create MOCKUP for AutoSchedule_Configuration (HTML) | Design | An Ngọc Anh | 2013-01-25 | 2013-01-26 | 6 | 0.75 |  |  |  |  | 0
[6 empty] | 0 |  |  |  |  | 0
SETUP

## Setup
Setup
| Category | Employee
| Design | Nguyễn Hoàng Việt Khánh
| Coding | Nguyễn Thị Yên Thịnh
| Testing | Nguyễn Đỗ Vượng
| Planning | An Ngọc Anh
Reporting
Research
PROJECTS